## Summary
Metro Navigator - QA Testing Summary Report
Manual QA testing performed on the AI-Powered Metro Bus Navigator (Flutter / Flask / SQLite)
1. Test Case Summary by Module
Module | Total Test Cases | Passed | Failed | Pass Rate | Notes
Login | 6 | 4 | 2 | 67% | 2 open bugs: Forgot Password not sending email, raw network error shown instead of friendly message
Route Search | 9 | 6 | 3 | 67% | All 3 failures found were fixed and closed after retest
TOTAL | 15 | 10 | 5 | 67%
2. Bug Report Summary
Module | Total Bugs | Open | Closed | High Severity | Medium Severity
Login | 2 | 2 | 0 | 1 | 1
Route Search | 4 | 0 | 4 | 3 | 1
TOTAL | 6 | 2 | 4 | 4 | 2
3. Key Defects Identified During Testing
Bug ID | Module | Summary | Severity | Status
BUG_001 | Login | Forgot Password does not send reset email | High | Open
BUG_002 | Login | Raw technical error shown instead of network error message | Medium | Open
BUG_003 | Route Search | Route generated for a non-existent station | High | Closed
BUG_004 | Route Search | Same source/destination produced a nonsensical route | High | Closed
BUG_005 | Route Search | Fare not calculated for Red-to-Orange Line transfer | High | Closed
BUG_006 | Route Search | Station matching failed for lowercase/spaced input | Medium | Closed
4. Overall Testing Stats
Total Modules Tested |  |  | 2
Total Test Cases Executed |  |  | 15
Total Bugs Found |  |  | 6
Bugs Fixed & Closed |  |  | 4
Bugs Still Open |  |  | 2
Route Search Pass Rate (post-fix, after retesting) |  |  | 100% (Login module still has 2 open defects, not yet fixed)